Clearance by MOD Civilian Searchers.

Details from files held in the RE Museum Archives.

Clearance operations carried out by 1 and 2 Troop (Civilian Searchers) 49 EOD Squadron RE. 1 July 1970 to 31 July 1971.

This reflects a part of the BD/EOD History that gets forgotten, which is the contribution to clearance work that these civilian teams made and still do.

Tasks completed or started during the period 1 July 1970 to 30 September 1970. Civilian Troops.

| Serial | Start | Est time Man Unit days | Est Completion | Unit | Details | Location | Civil Auth | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 74/Sussex/86 1 | 2 Jul 70 | 8 | 3 Jul 70 | 2 Tp 49 EOD Sqn | UXO Clearance with mine detectors | Calluna Nyetimber Lane West Chiltington, Sx 182/0913167 | DLA Canterbury | Searched no finds. |
| 24/Dorset/7 2 | 24 Jul 70 | 120 | 6 Aug 70 | 2 Tp 49 EOD Sqn | UXO Clearance with mine detectors | Lulworth Ranges Dorset 178/853803 | DLA Dorchester | 19 Acres searched 118 UXO found |
| 34/Hampshire/23 3 | 2 June 70 | 1798 | 19 Aug 70 | 2 Tp 49 EOD Sqn | UXO Clearance with mine detectors | Pirbright/Bisley Ranges Aldershot 169/930585 | DLAs Aldershot, London and Fareham | 472 acres searched 1159 UXOs recovered |
| 81/Wiltshire/16 4 | 10 Aug 70 | 60 | 14 Aug 70 | 2 Tp 49 EOD Sqn | UXO Clearance with mine detectors | New Farm, Chisledon, Wilts 157/193782 | DLA Durrington | 6 acres cleared 26 UXOs recovered |
| 81/Wiltshire/16 5 | 11 Jun 70 | 285 | 7 Jul 70 | 2 Tp 49 EOD Sqn | UXO Clearance with mine detectors | Figsbury Rings, Winterbourne, Wiltshire. 167/188341 | DLA Durrington | 2 acres cleared, 26 UXOs recovered. |
| 81/Wiltshire/16 6 | 14 Sept 70 | 100 | 18 Sept 70 | 2 Tp 49 EOD Sqn | UXO Clearance with mine detectors |  | DLA Durrington | 2.5 acres cleared, no finds |
| 39/Kent/66 7 | 21 Aug 70 | 48 | 26 Aug 70 | 2 Tp 49 EOD Sqn | UXO Clearance with mine detectors | St Nicholas Court, Farms Ltd. St Nicholas at Wade, Birchington, Kent. 173/260669 | DLA Canterbury | 11.5 acres cleared 3 x A/Tk mines Mk IV recovered |
| 72/Suffolk/27 8 | 28 Aug 70 | 10 | 28 Aug 70 | 2 Tp 49 EOD Sqn | UXO Clearance with mine detectors | St Olaves, Lowestoft, Suffolk 137/464989 | DLA Newmarket | 1.5 acres cleared 15 UXOs recovered |
| 46/Lincs 10 9 | 7 Jul 70 | 132 | 10 Sep 70 | 1 Tp 49 EOD Sqn | UXO Clearance with mine detectors and river bed by EOD Divers | Beckingham Ranges, nr Newark, Trent, Lincolnshire 113/8754 | DLA Grantham | 58 acres cleared 646 UXO recovered |
| 81/Wilts/ 7 10 | 24 Aug 70 | 429 | 11 Sep 70 | 2 Tp 49 EOD Sqn | UXO Clearance with mine detectors | Inber Ranges, Salisbury, Wilts 167/966485 | DLA Durrington | 68 UXOs recovered |
| 81/Wilts/ 7 11 | 17 Sep 70 | 40 | 18 Sep 70 | 2 Tp 49 EOD Sqn | UXO Clearance with mine detectors | Orcheston Dow, Larkhall Range, Salisbury, Wilts. 167/093472 | DLA Durrington | 6 acres cleared nil finds |
| 72 Suffolk/26 13 | 4 Aug 70 | 40 | 7 Aug 70 | 1 Tp 49 EOD Sqn | UXO Clearance with mine detectors | Pytchers Road, Woodbridge, Suffolk 136/273496 | DLA Newmarket | 5.5 acres cleared nil finds |
| 54/Norfolk/14 14 | 24 Aug 70 | 126 | 17 Sep70 | 1 Tp 49 EOD Sqn | UXO Clearance with mine detectors and Armoured dozer | Salthouse, Shingle Banks, Salthouse, Norfolk. 125/061450 | DLA Newmarket | 25 acres cleared 1 UXO recovered |
| 501 15 | 27 Aug 70 | 12 | 27 Aug 70 | 2 Tp 49 EOD Sqn | Assistance Dover Police locating murder weapon with mine detector | Dover Police, Kent | Dover Police | Nil finds |
| 501 16 | 14 Aug 70 | 4 | 14 Aug 70 | 2 Tp 49 EOD Sqn | UXO Search by EOD Divers. | Cliffe Hill Quarry, Markfield nr Coalville, Leics 121/485104 | DLA Grantham | 4000 Sq Feet searched nil finds |
| 39/Kent/ 68 | 30 Sep 70 | 1 | 30 Sep70 |  |  | 4 Goudhurst Close, Maidstone, Kent 172/747568 | DLA Canterbury | 4000 Sq Feet of Gardens searched nil finds |
| 83/Yoks/21 18 | 25 Nov 70 | 1085 | Late 70 | 1 Tp 49 EOD Sqn | UXO Search with mine detectors | Pockstone Moor, nr Pateley Bridge, Yorkshire 91/109604 | DLA Catterick | Up to date 348 acres searched 401 UXO recovered |
| 10/Brewknock/6 19 | 25 Nov 70 | 450 | Nov 70 | 1 Tp 49 EOD Sqn | UXO Search with mine detectors | Llanstock Range, Breconshire. 141/173159 | DLA Brecon | 127 acres searched 401 UXOs recovered |
| 83/Yorks/17 20 | 17 Jul 70 | 700 | 1974 | 1 Tp 49 EOD Sqn | UXO Search with mine detectors | Newton House Estate, Whitby, Yorks. 93/895020 | DLA Catterick | 452 Acres cleared nil finds |
| 72/Suffolk, 5 21 | 29 Apr 70 | 1200 | 1974 | 1 Tp 49 EOD Sqn | UXO Search with mine detectors | Orford Trg Area, Orford, Suffolk 150/426631 | DLA Newmarket | 2126 acres cleared 3845 UXOs recovered. |
| 72/Suffolk/ 28 22 | 21 Sep 70 | 60 | End Oct 70 | 1 Tp 49 EOD Sqn | UXO Search with mine detectors and Armoured dozer | Hopton Sea Defences, Hopton, Suffolk | DLA Newmarket | 4 acres cleared nil finds |
| 83/Yorks/19 23 | 18 Apr 70 | 140 | Mid 70 | 1 Tp 49 EOD Sqn | UXO Search with mine detectors | Dunscombe Park, Helmsley, York. 92/6082 | DLA York | 8602 UXO recovered. |
| 54/Norfolk. 38 24 | 24 Sep 70 | 60 | End Oct 70 | 1 Tp 49 EOD Sqn | UXO Search with mine detectors | Overy Marshes, nr Burnham Overy, Norfolk. 125/869452 | DLA Newmarket | 2 acres cleared 377 UXO recovered |
| 83/Yorks/19 25 | 26 Sep 68 | 60 | Late 71 | 2 Tp 49 EOD Sqn | UXO Search with mine detectors | Lydd Ranges, Kent 184/070184 | DLA Canterbury | 89 acres cleared 1078 UXO recovered |
| 34/Hampshire/23 26 | 7 Sep 70 | 900 | End Oct 70 | 2 Tp 49 EOD Sqn | UXO Search with mine detectors | Pirbright/Bisley Ranges, Deepcut Ranges, Aldershot, Hants 169/913585 | DLAs Aldershot, London, Fareham | Secons stage of clearance. 30 acres cleared 224 UXO recovered |
| 72/Suffolk/24 27 | 6 Oct 70 |  | Mid 71 | 1 Tp 49 EOD Sqn | UXO Search with mine detectors and Armoured Dozer | Minsmere Beach nr Dunwich, Suffolk 169/479702 | DLA Newmarket | 27 acres cleared no finds |
| 24/Dorset/32 28 | 27 May 70 | 400 | Nov 70 | 2 Tp 49 EOD Sqn | UXO Search with mine detectors | Firing range Oakford Hill, Oakford, Fitzpaine Dorset. 178/807093 | DLA Dorchester | 46 acres cleared 12 UXO recovered |
| R6/3/3 | 31 Jul 70 | 10 | 31 Jul 70 | 2 Tp 49 EOD Sqn | UXO Tasking Shafting | Radstock Farm, Earley, NR Reading, Berks | DLA Oxford | 1 a 250kg bomb recovered. Further work for suspected ? |
| R8/3/52 | 18 Aug 70 | 6 | 18 Aug 70 | 2 Tp 49 EOD Sqn | UXO Task | Building Site, Vicarage Rd, Westham, London | DLA London | 1 x 112kg Incendiary Oil bomb recovered. |
| 501 | 13 Aug 70 | 4 | 13 Aug 70 | 2 Tp 49 EOD Sqn | UXO Task | Salisbury Trg Area, Salisbury, Wilts | DLA London | 1 x 500lb Brit bomb recovered |
| R7/3/58/1 | 28 Aug | 70 | 110 | 2 Tp 49 EOD Sqn | UXO Task | Building Site of New Power Station, Isle of Grain, Kent 172/891768 | DLA Canterbury | 3 a 112ln brit bombs recovered. |
| R8/3/53 | 27 Aug 70 | 90 | 3 Sep 70 | 2 Tp 49 EOD Sqn | UXO Task | Roughet House, Whitehills, Bletchingley, Surrey 170/338529 | DLA Aldershot | 4 x 250kg recovered from a crashed 217 ET Dornier |
| R11/3/3 | 18 Sept 70 | 4 | 18 Sep 70 | 2 Tp 49 EOD Sqn | UXO Task | Hobbs Quarry Stormy Down, Bridgend, South Wales 153/849871 | DLA Brecon | 1 a 250kg SG UXB recovered |
| R8/4/57 | 19 Sep 70 | 4 | 19 Sep 70 | 2 Tp 49 EOD Sqn | UXO Task | Dyrham Park Farm, Potters Bar, Middx. 160/228991 |  | 1 x 50kg UXB recovered. |

- Total financial expenditure for civilian staff of EOD Unit RE for reporting period:-

July -              £22,806

August -         £18,046

September – £18,014

Total               £58,866

Costing of use of equipment and expenditure for Military personnel has not been calculated.

Tasks completed or started during the period 1 October 1970 to 31 December 1970. Civilian Troops.

| Serial | Start | Est time Man Unit days | Est Completion | Unit | Details | Location | Civil Auth | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 83/Yorks/17 1 | 17 Jul 67 | 740 | 1974 | 1 Tp 49 EOD Sqn | UXO Search with mine detectors | Newton House, Whitby, Yorks 93/895020 | DLA Catterick | 65 acres searched 1 UXO recovered |
| 83/Yorks/19 2 | 18 Apr 70 | 125 | 22 Oct 70 | 1 Tp 49 EOD Sqn | UXO Search with mine detectors | Dunscombe Park, Helmsley, Yorks. 92/6082 | DLA York | 59 acres cleared 9212 UXO recovered |
| 43/Lancs/10 1 | 27 Oct 70 | 765 | 17 Dec 70 | 1 Tp 49 EOD Sqn | UXO Search with mine detectors | Stanton Ground Quarries, Broughton, Lancs 88/220934 | DLA Chester | 53 acres searched 432 UXO recovered |
| 72/Suffolk/5 4 | 26 Apr 70 | 575 | 1974 | 1 Tp 49 EOD Sqn | UXO Search with mine detectors | Orford Trg Area, Orford, Suffolk 150/426631 | DLA Newmarket | 45 acres searched, 6 UXO recovered |
| 19/Brecknock/6 5 | 1 Apr 70 | 595 | 13 Nov 70 | 1 Tp 49 EOD Sqn | UXO Search with mine detectors | Llangattock Range, Brecknockshire. 141/1731159 | DLA Brecon | 158 acres searched 2545 UXO recovered |
| 54/Norfolk/28 6 | 24 Sep 70 | 45 | 22 Oct 70 | 1 Tp 49 EOD Sqn | UXO Search with mine detectors | Overy Marshes, nr Burham, Overy 125/869452 | DLA Newmarket | 9.5 acres cleared 507 UXO recovered |
| 72/Suffolk/28 7 | 21 Sep 70 | 40 | 29 Oct 70 | 1 Tp 49 EOD Sqn | UXO Search with mine detectors | Hopton Sea Defences, Suffolk 137/535000 | DLA Newmarket | 11.5 acres searched nil finds |
| 39/Kent/29 8 | 26 Sep 70 | 260 | Late 71 | 2 Tp 49 EOD Sqn | UXO Search with mine detectors | Llydd Ranges, Kent. 184/070184 | DLA Canterbury | 20 acres cleared 6 UXO recovered |
| 34/Hampshire/23 9 | 23 June 70 | 450 | 16 Oct 70 | 2 Tp 49 EOD Sqn | UXO Search with mine detectors | Pirbright/Bisley Ranges Aldershot 169/930585 | DLAs Aldershot and London |  |
| 81/Wilts/10 10 | 19 Oct 70 | 315 | 23 Oct 70 | 2 Tp 49 EOD Sqn | UXO Search with mine detectors | Manor Farm, Longbridge, Deverill, Wilts 166/8640 | DLA Durrington | 24 acres searched 14 UXOs recovered |
| 81/Wilts/6 | 15 May 68 | 845 | Dec 71 | 2 Tp 49 EOD Sqn | UXO Search with mine detectors | Beaches Barn, Trg Area, Bulford, Wilts 167/1949 | DLA Durrington | Up to date 721 acres searched 1922 UXO recovered |
| 54/Norfolk/13 12 | 28 Oct 70 | 12 | 28 Oct 70 | 2 Tp 49 EOD Sqn | UXO Search with mine detectors | Horsey Gap, Happisburg, Norfolk. 126/398299 | DLA Newmarket | 1000 sq yards searched no finds |
| 24/Dorset/ 32 13 | 27 May 70 | 500 | 27 Nov 70 | 2 Tp 49 EOD Sqn | UXO Search with mine detectors | Field Firing Range. Oakford, Fitzpaine, Dorset 178/807093 | DLA Dorchester | 20 acres searched 46 UXO recovered |
| 86/London/1 14 | 5 Nov 70 | 43 | 7 Nov 70 | 2 Tp 49 EOD Sqn | UXO Search with mine detectors | Woolwich Arsenal, London SE 18 171/458799 | DLA London District | 1.25 acres searched 46 UXO recovered |
| 39/Kent/64 15 | 20 Aug 70 | 22 | 4 Nove 70 | 2 Tp 49 EOD Sqn | UXO Search with mine detectors | Hunton Court Public Park, Wes Malling, Kent 171/623568 | DLA Canterbury | 300 Sq yards searched 5 UXO recovered. |
| 39/Kent/64 16 | 9 Sept 70 | 22 | 4 Nove 70 | 2 Tp 49 EOD Sqn | UXO Search with mine detectors | East Hill Farm, Kemsing, Kent 171/623568 | DLA Canterbury | 6 acres searched 2 UXO recovered |
| 83/Worcester/2 17 | 18 Nov 70 | 75 | 24 Nov 70 | 2 Tp 49 EOD Sqn | EOD Divers and Search for UXO | HM Borstal, Hewll Grange, Redditch, Wors. 131/009691 | DLA Shrewsbury | 243 UXO AND 18300 SAA recovered from the Lake |
| 40/Kincardine/ 3 18 | 10 Nov 70 | 445 | March 71 | 2 Tp 49 EOD Sqn | UXO Search with mine detectors | Hill of Fare, Aberdeenshire 40/700023 | DLA Dunfermline | 40 acres searched 1 UXO recovered |
| 8/Derkshire/7 19 | 21 Dec 70 | 20 | 22 Dec 70 | 2 Tp 49 EOD Sqn | UXO Search with mine detectors | Poor Ridge Cottage, Finchampstead, Berks | DLA Oxford | ½ searched nil finds |
| 24/Dorset/34/20 | 30 Nov 70 | 195 | 15 Dec 70 | 2 Tp 49 EOD Sqn | UXO Search with mine detectors | Sydling Stree, Nicholas Rifle Range, Dorset 178/641107 | DLA Dorchester | 43 acres searched 6 UXO and 35 SAA recovered. |
| 83/Yorks/9 21 | 1952 | 165 | Mid 71 | 2 Tp 49 EOD Sqn | UXO Search with mine detectors | Flyingdales Moor, Scarborough, Yorks | DLA York | In reporting period 12 acres searched nil finds |
| 24/Dorset/35 22 | 13 Oct 70 | 9 | 15 Oct 70 | 2 Tp 49 EOD Sqn | Excavation by Drott for suspect UXO | Acreman St, TA Centre, Sherborne, Dorset 178/636167 | DLA Dorchester | 45 ft x 21 ft x 3ft excavated nil finds |
| 39/Kent/67 23 | 1 Oct 70 | 11 | 1 Oct 70 | 2 Tp 49 EOD Sqn | UXO Search with mine detectors | Denne, Lower Mersham, Kent 173/636167 | DLA Canterbury | 1026 sq yards searched 1 A/T MH II Mine recovered |
| 39/Kent/68 24 | 1 Oct 70 |  | 1 Oct 70 | 2 Tp 49 EOD Sqn | UXO Search with mine detectors | 4 Gouldhurst Close, Maidstone, Kent 172/747568 | DLA Canterbury | 80ft x 50ft searched nil finds |
| 8/Wilts/7 25 | 29 Oct 70 | 12 | 29 Oct 70 | 2 Tp 49 EOD Sqn | UXO Search with mine detectors | Larkhill Ranges, Salisbury, Wilts 167/114476 | DLA Durrington | 100m x 100msearched nil finds |
| R6/3/31 26 | 31 Jul 70 | 210 | 12 Nov 70 | 2 Tp 49 EOD Sqn | Suspected UXO Shafting and Borehole | Radstock Farm, Earley, Reading, Berks. | DLA Oxford | Discredit |
| R1//3/7 27 | 7 Oct 70 | 20 | 12 Oct 70 | 2 Tp 49 EOD Sqn | UXO Task | Brunel Park, Watcombe, Torquay, Devon. 188/3360 | DLA Plymouth | Discredit. Geological fault in rock strats. |
| R12/3/9 28 | 9 Nov 70 | 205 | 8 Dec 70 | 1 Tp 49 EOD Sqn | UXO Task | Doe Bank Farm, Holt Fleet, Ombersley, Druitwich, Worcs. 130/828634 | DLA Shrewsbury | Discredit |
| R7/3/69 29 | 5 Nov 70 | 6 | 6 Nov 70 | 2 Tp 49 EOD Sqn | UXO Task | Hedge Pace Road, Stone, Dartford, Kent. 171/584738 | DLA Canterbury | 1 x 250kg Bomb recovered |
| 501 20 | 19 Oct 70 | 2 | 19 Oct 70 | 1 Tp 49 EOD Sqn | UXO Task | Town Marshes, Orford, Suffolk 150/435500 | DLA Newmarket | 1 x 112lb British RH Bomb 1914-19 recovered |
| R10/3/38 32 | 4 Nov 70 | 50 | 11 Nov 70 | 1 Tp 49 EOD Sqn | UXO Task | Tunfield Estate, Hoddeston, Herts | DLA Shrewsbury | Discredit |
| R8/3/60 32 | 16 Nov 72 | 92 | 11 Dec 70 | 2 Tp 49 EOD Sqn | UXO Task Borehole by Boyles Rig | Thessaly Road, Wandswoth, London, SW7 | DLA London | Discredit |
| R7/3/66 33 | 30 Nov 70 | 8 | 1 Dec 70 | 2 Tp 49 EOD Sqn | UXO Task | HM Prison, Holloway, London N7 | DLA London | Discredit |
| R7/3/74 34 | 30 Nov 70 | 4 | 30 Nov 70 | 2 Tp 49 EOD Sqn | UXO Task | SS Vective Isle Sheerness, Kent | DLA Canterbury | 1 x 250lb naval shell (1835) recovered |
| R14/3/31 35 | 14 Dec 70 | 55 | 18 Dec 70 | 1 Tp 49 EOD Sqn | UXO Task | Nanby Farm, Cadeby, nr Leicester 121/435024 | DLA Grantham | Further work required |

*Total Financial Expenditure for Civilian Staff of EOD Unit RE for the Reporting Period was;-

October 1970 –    £22,559

November 1970 - £16,494

December 1970 - £15,796

Costing of use of Equipment and Expenditure for Military Personnel has not been calculated.

Tasks completed or started during the period 1 January 1971 to end of March 1970. Civilian Troops.

Page 1 of 9 entry’s not readable

| 81/Wilts/6 | (15 May 1968) 20 Feb 71 | 728 | (Dec 71) 24 Mar 71 | 2 Tp 49 EOD Sqn | UXO Search with mine detectors | Berches Barn, Trg are, Bulford, Wilts. 167/1949 | DLA Durrington | 30 acres cleared, 38 UXO recovered |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 39/Kent 29 | 1 Mar 71 | 728 | 26 Mar 71 | 2 Tp 49 EOD Sqn | UXO Search with mine detectors | Llyd Ranges, Kent 184/070184 | DLA Canterbury | 21 acres cleared 22 UXO recovered |
| 43/Lancashire/11 |  |  |  | 1 Tp 49 EOD Sqn | UXO Search with mine detectors | Atomic Energy Authority Site, Hoysham, Lance 94/ | DLA Chester | Nil finds |
| 501 | 22 Mar 71 | 12 | 23 Mar 71 | 2 Tp 49 EOD Sqn | UXO Search with mine detectors | 30 mtr Range, Bushfield Camp, Winchester, Wilts 168/469273 | DLA Durrington | 10 acres cleared no finds |
| 74/Sussex/26 |  |  |  | 2 Tp 49 EOD Sqn | UXO Search with mine detectors | Baseldean Farm, Woodingdean, Sx 183/375042 | DLA Canterbury | Track Area cleared |
| 81/Wilts/7 | 24 Mar 71 |  | 30 Mar 71 | 2 Tp 49 EOD Sqn | UXO Search with mine detectors | Quebec Barn, Knookdown, Nr Chitterne, Wilts 167/ | DLA Durrington | 18 acres cleared 176 UXO cleared |
| 22/Derby/5 | 19 Jan 71 |  | 28 Jan 71 | 1 Tp 49 EOD Sqn | UXO Search with mine detectors | Marketon Park, Derby 120/3337 | DLA Grantham | 12 acres cleared. 42 UXO recovered. |
| R4/3/29 | 10 Feb 71 | 2 | 10 Feb 71 | 2 Tp 49 EOD Sqn | Suspected UXO | Arreton Manor, Newport I of W 180/514868 | DLA Fareham, Hants | Discredit |
| R5/3/17 | 12 Jan 71 | 5 | 12 Jan 71 | 2 Tp 49 EOD Sqn | Suspected UXO | Brandy Bottom, Winslade, nr Basingstoke, Hants | DLA Fareham | 1x 150lb British bomb recovered |
| R5/3/25 | 2 Feb 71 | 2 | 2 Feb 71 | 2 Tp 49 EOD Sqn | Suspected UXO | 2 Spokeane Close, Aldershot, Hants 169/859498 | DLA Fareham | Discredit |
| R7/3/77 | 9 Feb 71 | 2 | 9 Feb 71 | 2 Tp 49 EOD Sqn | Suspected UXO | New Factory Site, Spinney Lane, Aylsham, Kent 173/232517 | DLA Canterbury | Discredit |
| R7/3/78 | 2 Mar 71 | 2 | 2 Mar 71 | 2 Tp 49 EOD Sqn | Suspected UXO | Rabbits Farm, South Darenth, Kent 171/579690 | DLA Canterbury | Discredit |
| R9/3/20 | 16 Feb 71 | 4 | 16 Feb 71 | 2 Tp 49 EOD Sqn | Suspected UXO | Rolls Farm, Tollesbury, Essex. 162/942078 | DLA Newmarket | 9 up to 1000lb bomb recovered |
| R10/3/41 | 19 Feb 71 | 3 | 19 Feb 71 | 1 Tp 49 EOD Sqn | Suspected UXO | Norton Park, Watton, Norfolk 136/911481 | DLA Newmarket | 2 x bombs inert practice recovered. |
| R14/3/3 | 18 Jan 71 | 550 | 26 Mar 71 | 1 Tp 49 EOD Sqn | Suspected UXO | Nanby Farm, Cadby, ne Leicester 121/435024 | DLA Grantham | Borehole using Boles Rig. Further work necessary |

**Total Financial Expenditure for Civilian Staff of EOD Unit RE for the Reporting Period was;-

January 1971 -   £19,706

February 1971 - £15,541

March 1971 -     £17,352

Total -                  £52,599

Costing of use of Equipment and Expenditure for Military Personnel has not been calculated.

Tasks completed or started during the period 1 April 1971 to 30 July 1971. Civilian Troops.

| 43/Lancs/11 | 23 Mar 71 | Wef 1 Apr 71 150 | 7 Apr 71 | 49 EOD Sqn | Detector Search | Nuclear Power Station, Heysham, Lancs | DLA Chester | Ni finds |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 62/Radnorshire/4 | 14 April 71 | 203 | 22 April 71 | 49 EOD Sqn | 2 ½ survey check only | Imperial Metal Industries, (Kynok) Ltd New Radnor, Radnorshire 128/175615 | DLA Brecon |  |
| 83/Yorks/21 | 26 Apr 71 | 5000 | 30 Jun 71 | 49 EOD Sqn | Detector Search | Pckstone Moor, Nr Pateley Bridge, Yorks 91/100604 | DLA Catterick | 138 acres searched 204 UXO recovered |
| 3/Angus/1 | 22 Apr 71 | 1040 | 18 June 71 | 49 EOD Sqn | Detector Search | Barry Buddon Range, Angus 50/550320 | DLA Dunfermline | 44 acres cleared 720 UXO recovered |
| 52/Morayshire/5 | 27 Apr 71 | 72 | 4 May 71 | 49 EOD Sqn | Detector Search | Lower Henpriggs Farm, nr Kinloss, Morayshire 29/098645 | DLA Dunfermline | 2 acrescleared no finds |
| 72/Suffolk/5 | 5 Apr 71 | Wef 1 Apr 71 240 | 16 Apr 71 | 49 EOD Sqn | Detector Search | Orford Trg area, Orford, Suffolk 150/426631 | DLA Newmarket | 17 acres searched 9 UXO recovered |
| 54/Norfolk/29 | 22 Apr 71 | 275 | 28 May 71 | 49 EOD Sqn | Detector Search | Marsh Far, Burnham Overy, nr Durnhan Market, Norfolk 125/8644 | DLA Newmarket | 30 acres searched 206 UXO recovered |
| 74/Sussex/26 | 30 Mar 71 | 66 | 5 May 71 | 49 EOD Sqn | Detector Search | Balsdean Farm, Dazehill Road, Woodindean, Brighton, Sx 183/375042 | DLA Fareham | 2 acres cleard 70 UXO recovered further work required |
| 36/London/1/2 | 29 Apr 71 | 900 | 25 Jun 71 | 49 EOD Sqn | Detector Search | Woolwich Arsenal, London SW18 | DLA London | 30 acres cleared 2459 UXO recovered |
| 81/Wilts/6 | 17 May 71 | 155 | 21 May 71 | 49 EOD Sqn | Detector Search | Beaches Barn Trg Area, Bulford Wilts 167/ | DLA Durrington | 22 acres searched 8 UXO recovered |
| 16/Cardiganshire/2 | 11 May 21 | 32 | 12 May 71 | 49 EOD Sqn | Detector Search | Llanerch Bontoch, Aberystwyth, Cardiganshire 127/707856 | DLA Brecon | 10% spot check of 35 acres nil finds |
| 69/Somerset/8 | 7 May 71 | 525 | 9 Jul 71 | 49 EOD Sqn | Detector Search and EOD Diver Search | Apec Recreation Park, Burnham on Sea, Somerset 165/310475 | DLA Dorchester | 14 acres searched 1327 UXO recovered |
| 81/Wilts/5 | 3 May 71 | 320 | 14 May 71 | 49 EOD Sqn | Detector Search | Liddington Hill, nr Chisledon, Wilts 157/310475 | DLA Durrington | 60 acres cleared, 93 UXO recovered. Further work necessary |
| 70/Staffordshire/3 | 5 Apr 71 | 3 | 5 Apr 71 | 49 EOD Sqn | Excavation of a bunker and detector search | Corporation Ground, Wolverhampton, Staffordshire. 130/888900 | DLA Staffordshire | Bunker excavated and area searched. 168 AW bomb recovered. |
| 73/Surrey/16 | 17 May 71 | 180 | 28 May 71 | 49 EOD Sqn | Detector Search | Bury Hill Estate, Dorking, Surrey 170/156483 | DLA Aldershot | 20 acres cleared 8 UXO recovered. Further work necessary |
| 24/Dorset/7 | 24 May 71 | 144 | 4 Jun 71 | 49 EOD Sqn | Detector Spot Check | Lulworth Camp, Dorset 178/829807 | DLA Dorchester | 100 acres spot checked 14 UXO and 9cwt of scrap recovered |
| 39/Kent/29 | 7 Jun 71 | 119 | 15 Jun 71 | 49 EOD Sqn | Detector Search | Llydd Ranges, Kent 184/070184 | DLA Canterbury | 10 acres searched nil finds |
| 26/Dunbarton/3 | 21 Jun 71 | 300 | 1 Jul 71 | 49 EOD Sqn | Detector Search | Merkins Farm, Garocharn, Dumbartonshire 60/423802 | DLA Dunfermline | 400 acres 2 % spot checked nil finds |
| 54/Norfolk/14 | 15 Jun 71 | 90 | 24 Jun 71 | 49 EOD Sqn | Armoured Dozer | Coast Protection Works, Salthouse, Norfolk 125/062450 | DLA Newmarket | 25 acres cleared no finds |
|  | 19 May 71 | 6 | 19 May 71 | 49 EOD Sqn | Detector Search | 14 Marine Drive, Goring Sx | DLA Canterbury | 700 Sq yards searched nil finds |
| 72/Suffolk/29 | 24 May 71 | 22 | 25 May 71 | 49 EOD Sqn | Detector Search | Droxted Estate, Sutton Common, Suffolk 150/314475 | DLA Newmarket | 4 acres cleared. 62 UXO recovered |
| 39/Kent/29 | 16 Jun 71 | 150 | Jul 71 | 49 EOD Sqn | Detector Search | 94mm Rifle Grenade Range, Llydd, Kent 184/ | DLA Canterbury | 6 acres searched 26 UXO recovered |
| 39/Kent/26 | 28 Jun 71 | 99 | Jul 71 | 49 EOD Sqn | Detector Search | Wouldham Quarry, Kent 172/718623 | DLA Canterbury | 20 acres cleared 2 UXO recovered |
| 74/Sussex/66 | 23 Jun 71 | 23 Jun 71 |  | 49 EOD Sqn | Detector Search | RARDE, Langhurst, Horsham, Sussex 182/180355 | DLA | Checking area for metal |
| R8/3/66 | 22 Mar | 130 | 22 Apr | 49 EOD Sqn | Detector Search | HM Prison Holloway, London. N7 | DLA London | Discredit no trace of UXO |
| R8/3.73 | 26 Apr 71 10 May 71 | 12 | 29 Apr 71 13 May 71 | 49 EOD Sqn | Bore-hole | Castle Bar Mews, Ealing London W5 | DLA London | Discredit no trace of UXO |
| R9/3/22 | 31 May 73 | 138 | Jul 71 | 49 EOD Sqn | Detector Search | Shoebury Cottage, Shoebury Common Road, Southend-on-Sea, Essex | DLA Newmarket | Work in hand |
| R10/3/48 | 14 Jun 71 | 90 | Jul 71 | 49 EOD Sqn | Detector Search | Elsing Bridge, Dereham, Norfolk | DLA Newmarket | Work in hans |
| R12/3/11 | 5 May 71 | 12 | 6 May 71 | 49 EOD Sqn | Detector Search | Building site, Coles Hill Street, Birmingham | DLA Shrewsbury | 1 x 50 kb bomb recovered. |

No further details in the file.